## Issue_Tracker
PROJECT NAME |  |  | Critical: 0 |  | PENDING | % |  | TOTAL
SauceLab |  |  | High: 1 |  | 5 | 100% |  | 5
Sr Test Engineer |  |  | Medium: 3 |  | IN PROGRESS | %
Rupa Mandal |  |  | Low: 1 |  | 0 | 100%
PROJECT OWNER |  |  |  |  | CLOSED | %
XXXXXX |  |  |  |  | 0 | 100%
Sr No | Defect ID | Funtionality | Responsible | Severity | Status | Opened On | Closed On | DESCRIPTION | Expected | Actual | Reproduce Steps
1 | Issue 1 | Inventory Page | Richard Allen | Low | Pending | 2025-05-05 |  | Description 1 | User should able to login without any popup | Popup is coming as change your password with no change option | Step1: Go to the SwagLabs login page Step2: Give username and password and click on the login button Step3: After login user will able to see the popup coming as change the password
2 | Issue 2 | Cart Page | Louise Burke | Medium | Pending | 2025-05-05 |  | Description 2 | Quantity should be editable | Quantity in not editable in the your cart page | Step1: Go to the SwagLabs login page Step2: Give username and password and click on the login button Step3: After login add items to "your cart" Stem4: Click on the cart icon it will navigate you to "your cart" page Stem5: Under quantity numbers are not editable
3 | Issue 3 | Overview page | Bill House | Medium | Pending | 2025-05-05 |  | Description 3 | Decimal digits should be consistent | Decimal digits are not consistent | Step1: Go to the SwagLabs login page Step2: Give username and password and click on the login button Step3: After login add items to "your cart" Step4: Click on the cart icon it will navigate you to "your cart" page Step5: Click on the Checkout Button It will navigate you to the Checkout: Your Information Page Step6: Provide all the details then click on the continue button it will navigate you to the checkout: Overview page Step7: Under Item total decimal digits are not consistent
4 | Issue 4 | Cart Page | Viola Murray | High | Pending | 2025-05-05 |  | Description 4 | Doller currency sign should present in "your cart" page | Doller currency sign is missing in "your cart" page | Step1: Go to the SwagLabs login page Step2: Give username and password and click on the login button Step3: After login add items to your cart Stem4: Click on the cart icon it will navigate you to "your cart" page Stem5: Under description dollar currency sign is missing
5 | Issue 5 | Cart Page | Viola Murray | Medium | Pending | 2025-05-05 |  | Description 5 | With zero item in the cart should not move forward to checkout page | With zero item in the cart still moving forward to checkout page | Step1: Go to the SwagLabs login page Step2: Give username and password and click on the login button Step3: After login add items to "your cart" Step4: Click on the cart icon it will navigate you to "your cart" page Step5: Remove all the items from the cart Step6Click on the Checkout Button It will navigate you to the Checkout: Your Information Page Step7: Provide all the details then click on the continue button it will navigate you to the checkout: Overview page Step7: Under Item total decimal digits are not consistent
Low: 1
Medium: 3
High: 1
Critical: 0